## Gantt Chart Template
GANTT CHART TEMPLATE |  |  | To use the template click File and make a copy | [24 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Mayo/ASU Synapse: AI Empathy Tool |  |  |  |  | COMPANY NAME | [8 empty] | Team 19
| PROJECT MANAGER | Molly Svendson |  |  |  |  | DATE | [8 empty] | 2025-09-18
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | DT1
1.1 | DT 1 - Team Commitment and Charter | Team 19 | 2025-08-20 | 2025-09-05 | 15 | 100% | bar: WEEK 1 R to WEEK 3 F
1.1.1 | DT1 - Generating Insights | Team 19 | 2025-08-20 | 2025-09-12 | 22 | 100% | bar: WEEK 1 R to WEEK 3 F
2 | DT2
2.1 | DT2 - Gantt Chart | Team 19 | 2025-09-12 | 2025-09-18 | 6 | 100% | bar: WEEK 4 M to WEEK 5 F
2.2 | DT2 - Assignment Project Selection and Statement | Team 19 | 2025-09-12 | 2025-09-19 | 7 | 100% | bar: WEEK 4 M to WEEK 5 F; WEEK 8 R
2.3 | DT2 - Executive Summary | Team 19 | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 6 M to WEEK 6 F
2.4 | DT2 - Assignent Initial Design History File | Team 19 | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 6 M to WEEK 6 F
2.5 | DT2 - Assignment MDDI Technical Report | Team 19 | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 6 M to WEEK 6 F
2.6 | DT2 - Assignment Lab Notebook, Time Logs, Due Dilligence | Team 19 | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 6 M to WEEK 6 F
3 | DT3
3.1 | DT 3 - Assignment: Brainstorming Plan | Team 19 | 2025-09-26 | 2025-10-03 | 7 | 100% | bar: WEEK 7 M to WEEK 7 F
3.2 | DT 3 - Assignment: Competitive Benchmarking | Team 19 | 2025-09-26 | 2025-10-03 | 7 | 100% | bar: WEEK 7 M to WEEK 7 F
3.3 | DT 3 - Assignment: Concept Mapping and Analysis | Team 19 | 2025-09-26 | 2025-10-03 | 7 | 100% | bar: WEEK 7 M to WEEK 7 F
3.4 | DT 3 - Assignment: Needs Metric Table | Team 19 | 2025-09-26 | 2025-10-03 | 7 | 100% | bar: WEEK 7 M to WEEK 7 F
3.5 | DT 3 - Assignment: Survey Interview Questions (Team) | Team 19 | 2025-09-26 | 2025-10-03 | 7 | 100% | bar: WEEK 7 M to WEEK 7 F
3.6 | DT 3 - Assignment: Ethical Issues in Medical Device Design | Team 19 | 2025-10-03 | 2025-10-10 | 7 | 100% | bar: WEEK 8 M to WEEK 8 R
4 | DT4
4.1 | DT 4 - Assignment: Concept Iteration | Team 19 | 2025-10-10 | 2025-10-17 | 7 | 0%
4.2 | DT 4 - Assignment: Continued Benchmarking | Team 19 | 2025-10-10 | 2025-10-18 | 8 | 0%
4.5 | DT 4 - Assignment: Formal Design Reviews | Team 19 | 2025-10-10 | 2025-10-19 | 9 | 0%
4.4 | DT 4 - Assignment: Intellectual Property Discussion and Prior Art Search | Team 19 | 2025-10-10 | 2025-10-20 | 10 | 0%
4.5 | DT 4 - Assignment: Preliminary Business Model | Team 19 | 2025-10-10 | 2025-10-21 | 11 | 0%
5 | DT5
5.1 | DT 5 - Assignment: Advanced Concept Analysis | Team 19 | 2025-10-21 | 2025-10-31 | 10 | 0%
5.2 | DT 5 - Assignment: Final Concept Selection | Team 19 | 2025-10-21 | 2025-10-31 | 10 | 0%
5.3 | DT 5 - Assignment: House of Quality | Team 19 | 2025-10-21 | 2025-10-31 | 10 | 0%
5.4 | DT 5 - Assignment: Initial Screening | Team 19 | 2025-10-21 | 2025-10-31 | 10 | 0%
5.5 | DT 5 - Assignment: Initial Technical Model | Team 19 | 2025-10-21 | 2025-10-31 | 10 | 0%
5.6 | DT 5 - Assignment: Product Architecture | Team 19 | 2025-10-21 | 2025-10-31 | 10 | 0%
6 | DT6
6.1 | DT 6 - Assignment: Digital Posters | Team 19 | 2025-10-31 | 2025-11-14 | 14 | 0%
6.2 | DT 6 - Assignment: Graphical Abstract | Team 19 | 2025-10-31 | 2025-11-14 | 14 | 0%
7 | DT7
7.1 | DT 7 - Assignment: Bill of Materials | Team 19 | 2025-11-14 | 2025-11-26 | 12 | 0%
7.2 | DT 7 - Assignment: Groups of Authority | Team 19 | 2025-11-14 | 2025-11-26 | 12 | 0%
7.3 | DT 7 - Assignment: Refined Technical Model | Team 19 | 2025-11-14 | 2025-11-26 | 12 | 0%
7.4 | DT 7 - Assignment: Review Quality Systems Regulation (QSR) Analysis | Team 19 | 2025-11-14 | 2025-11-26 | 12 | 0%
8 | DT8
8.1 | DT 8 - Assignment: Design History File (DHF) Compilation | Team 19 | 2025-11-26 | 2025-12-10 | 14 | 0%
8.2 | DT 8 - Assignment: Binder | Team 19 | 2025-11-26 | 2025-12-12 | 16 | 0%
9 | BME 490 Assignments | Team 19 | 2026-01-01 | 2026-05-05 | 7 | 0%
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## Try Smartsheet
Try Smartsheet for Free